## Sheet1
Milestone | Module/Pages | Objective | Mitchell | Parisha | Promish | Jasmine | Date
Assessment | Question Bank Module |  | X | X |  |  | 2025-01-19
Assessment | English Question Bank Module |  | X | X |  |  | 2025-01-19
Assessment | Matching Question Bank Module |  | X | X |  |  | 2025-01-19
Assessment | Repetition Question Bank Module |  | X | X |  |  | 2025-01-19
Assessment |  | Verification and Validation Testing | X | X | X | X | 2025-01-19
Controllers | API Gateway |  |  |  | X |  | 2025-01-19
Controllers | App Controller |  |  |  | X |  | 2025-01-19
Controllers |  | Verification and Validation Testing | X | X | X | X | 2025-01-19
Assessment GUI | Assessment Selection Page |  |  |  |  | X | 2025-01-19
Assessment GUI | Parent Checklist Page |  |  | X |  |  | 2025-01-22
Assessment GUI | Input Check Page |  |  |  |  | X | 2025-01-22
Assessment GUI | Assessment Questions Page |  | X |  |  |  | 2025-01-22
Clinician Dashboard | Result Storage Module |  |  |  | X |  | 2025-01-22
Assessment GUI | Assessment Instructions Page |  |  | X |  |  | 2025-01-25
Assessment GUI | Tutorial Page |  | X |  |  |  | 2025-01-25
Assessment GUI | Assessment Completion Page |  |  |  |  | X | 2025-01-25
Assessment GUI |  | Verification and Validation Testing | X | X | X | X | 2025-01-25
Clinician Dashboard | Report Generation Module |  |  |  | X |  | 2025-01-25
Clinician Dashboard |  | Verification and Validation Testing | X | X | X | X | 2025-01-25
Clinician Dashboard GUI | Clinician Dashboard Overview Page |  | X |  |  |  | 2025-01-28
Clinician Dashboard GUI | Patient Overview Page |  |  | X |  |  | 2025-01-28
Clinician Dashboard GUI | Patient Assessment Results Analysis Page |  |  |  |  | X | 2025-01-28
Media Processing | Media Processing Module |  |  |  | X |  | 2025-01-28
Clinician Dashboard GUI | Bias Review Page |  |  |  |  | X | 2025-01-31
Clinician Dashboard GUI | Add New Client Page |  | X |  |  |  | 2025-01-31
Clinician Dashboard GUI |  | Verification and Validation Testing | X | X | X | X | 2025-01-31
Homepage | Authentication Module |  |  |  | X |  | 2025-01-31
Homepage GUI | Select Account Type Page |  |  | X |  |  | 2025-01-31
Homepage GUI | Login Page (Parent) Page |  |  | X |  |  | 2025-02-03
Homepage GUI | Login Page (Clinician) Page |  |  | X |  |  | 2025-02-03
Homepage GUI | Create Account Page |  | X |  |  |  | 2025-02-03
Homepage GUI | Homepage (Parent) Page |  |  |  |  | X | 2025-02-03
Homepage GUI |  | Verification and Validation Testing | X | X | X | X | 2025-02-03
Media Processing | Video Processing Module |  |  |  | X |  | 2025-02-03
Media Processing | Audio Processing Module |  | X |  |  |  | 2025-02-06
Media Processing |  | Verification and Validation Testing | X | X | X | X | 2025-02-06
Miscellaneous | Logging Module |  |  | X |  |  | 2025-02-06
Miscellaneous | Real-Time Feedback Module |  |  |  | X |  | 2025-02-06
Miscellaneous |  | Verification and Validation Testing | X | X | X | X | 2025-02-06
Admin | Add Clinician Page |  |  |  |  | X | 2025-02-06
Admin |  | Verification and Validation Testing | X | X | X | X | 2025-02-06
Rev0 |  | Full System Testing | X | X | X | X | 2025-02-08
Rev0 |  | Rev0 Practice | X | X | X | X | 2025-02-09
Rev0 |  | Rev0 Presentation | X | X | X | X | 2025-02-10
|  |  | 22 | 23 | 20 | 19